## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Green
Project: Green
Contoso, Ltd.
Riku Nakano
Project start date: | 2025-09-12 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | September | [6 empty] | October | [34 empty] | November
 | time axis 2025-09-25 to 2025-11-19
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-09-25 to 2025-11-19
Project development
Project charter |  | 25% | 2025-09-15 | 3
Research |  |  | 2025-09-20 | 1
Projections |  | 50% | 2025-09-12 | 10
Stakeholders |  |  | 2025-10-05 | 1 | bar: 2025-10-05
Review |  | 10% | 2025-09-21 | 6
Contracts
Proposals |  | 60% | 2025-09-21 | 13
Document review |  | 50% | 2025-09-22 | 9
Bid date |  | 33% | 2025-09-30 | 11
Award date |  |  | 2025-10-09 | 1 | bar: 2025-10-09
Finalize |  |  | 2025-10-10 | 24
Design
Feasibility study |  |  | 2025-09-30 | 4
Submit permit applications |  |  | 2025-10-04 | 14
Design proposal |  |  | 2025-10-20 | 6
Materials |  |  | 2025-11-02 | 3
Equipment |  |  | 2025-10-25 | 19
Testing
Environment |  |  | 2025-10-22 | 15
System test |  |  | 2025-10-14 | 5
Issues/bugs |  |  | 2025-12-04 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Blue
FYP
CarePlus - Healthcare System
Students: | Youssef Farah (202110800) | Tony Katrib (202112491) | Daniel Kabbout (202210815)
Project start date: | 2025-02-19 | [10 empty] | Scrolling increment: | [5 empty] | 0
Supervisor: | Dr. Joseph Gemayel |  |  |  | February | [13 empty] | March | [27 empty] | April
 | time axis 2025-02-19 to 2025-04-15
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-02-19 to 2025-04-15
Project Planning
Monorepo Initialization |  | 100% | 2025-02-19 | 8 | bar: 2025-02-19
Tools & Tech Stack Setup |  | 100% | 2025-02-20 | 3
Title 2
Task 1 |  | 60% | 2025-09-21 | 13
Task 2 |  | 50% | 2025-09-22 | 9
Task 3 |  | 33% | 2025-09-30 | 11
Task 4 |  |  | 2025-10-09 | 1
Task 5 |  |  | 2025-10-10 | 24
Title 3
Task 1 |  |  | 2025-09-30 | 4
Task 2 |  |  | 2025-10-04 | 14
Task 3 |  |  | 2025-10-20 | 6
Task 4 |  |  | 2025-11-02 | 3
Task 5 |  |  | 2025-10-25 | 19
Title 4
Task 1 |  |  | 2025-10-22 | 15
Task 2 |  |  | 2025-10-14 | 5
Task 3 |  |  | 2025-12-04 | 5
Task 4
Task 5

## Purple
Project: Purple
Contoso, Ltd.
Hayden Cook
Project start date: | 2025-09-12 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | September | [6 empty] | October | [34 empty] | November
 | time axis 2025-09-25 to 2025-11-19
Milestone description | Assigned to | Progress | Start | Days | time axis 2025-09-25 to 2025-11-19
Title 1
Task 1 |  | 25% | 2025-09-15 | 3
Task 2 |  |  | 2025-09-20 | 1
Task 3 |  | 50% | 2025-09-12 | 10
Task 4 |  |  | 2025-10-05 | 1 | bar: 2025-10-05
Task 5 |  | 10% | 2025-09-21 | 6
Title 2
Task 1 |  | 60% | 2025-09-21 | 13
Task 2 |  | 50% | 2025-09-22 | 9
Task 3 |  | 33% | 2025-09-30 | 11
Task 4 |  |  | 2025-10-09 | 1 | bar: 2025-10-09
Task 5 |  |  | 2025-10-10 | 24
Title 3
Task 1 |  |  | 2025-09-30 | 4
Task 2 |  |  | 2025-10-04 | 14
Task 3 |  |  | 2025-10-20 | 6
Task 4 |  |  | 2025-11-02 | 3
Task 5 |  |  | 2025-10-25 | 19
Title 4
Task 1 |  |  | 2025-10-22 | 15
Task 2 |  |  | 2025-10-14 | 5
Task 3 |  |  | 2025-12-04 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one